**County** SIM™ Professional Development and Coaching **Division Plan**

2018-2019

P Middle School and D Middle School

|  |  |  |  |
| --- | --- | --- | --- |
| Date | Time | Content | Who |
| June/July 2018  August 2018  \*Specific dates TBD  August 2018  Same date as above- TBD  August 2018  2nd week of school, TBD | 3 hour session  3 hour session  Planning periods | 1. Prepare student materials (folders and cue cards) 2. Preview expectations for writing instruction 3. Determine dates for PD and coaching for 1st semester 4. **Fundamentals** in the Sentence Writing Strategy (FSWS) 5. **Proficiency** in the Sentence Writing Strategy (PSWS): **Simple Sentences** 6. Small group coaching for FSWS & PSWS second week of school during planning periods. Scoring some of the pretest for PSWS during this time | Dr. T coordinates  **English 6 & 7 grade co-teachers** at DMS  Any new English 6 teacher and/or new co-teacher who has not received the PD at PMS  **English 8 teachers and their co-teachers** at DMS  **English 7 & any *new* English 8 grade English teachers and their co-teachers** at PMS  DMS & PMS English 6-8 and co-teaching partners |
| September 2018  Early release day, TBD | 1:30-4:30 p.m.  Planning periods | 1. Proficiency in the Sentence Writing Strategy: **Compound Sentences** 2. Class visits and debriefing during planning periods for FSWS & PSWS (Debrief will take place as soon as possible on the same day) | Location to TBD after school and bring DMS & PMS together  English 6, 7, 8 and their co-teachers at DMS & PMS  Dates for each school to TBD |
| October 2018, TBD | Planning periods | * Small group coaching during planning periods on Generalization of FSWS & ongoing coaching for PSWS | English 6, 7, and 8 grade teachers and their co-teachers at DMS |
| October 2018, TBD  October 2018, TBD | 3 hour session  Planning periods | 1. PD on The Paragraph Writing Strategy: **Topic Sentences** 2. Small group coaching during planning periods for FSWS & PSWS | English 8 teachers and their co-teachers at PMS  English 8 teachers and their co-teachers at PMS |
| November 2018, TBD | Planning periods | * Class visits and debriefing during planning periods for FSWS and PSWS (Debrief will take place as soon as possible on the same day) | English 6, 7, 8 teachers and their co-teachers at DMS |
| November 2018, TBD | 3 hour session  Planning periods | 1. PD on The Paragraph Writing Strategy: **Detail Sentences** 2. Class visits and debriefing during planning periods for Topic Sentences (Debrief will take place as soon as possible on the same day) | English 8teachers and their co-teachers at PMS  English 8 teachers and their co-teachers at PMS |
| January 2019, TBD | 3:30-4:45 p.m.  Planning periods | 1. After school PD session on The Paragraph Writing Strategy: **Clincher Sentences** 2. Small group coaching during planning periods for Detail Sentences | English 8 teachers and their co-teachers at PMS |
| January 2019, TBD | Planning periods | * Small group coaching during planning periods for Generalization of PSWS and preparing for writing SOL | 8th grade English teachers and their co-teachers at DMS |
| February 2019, TBD | Planning periods | * Paragraph Writing coaching and preparing for 8th grade writing SOL | English 7th & 8th grade & co-teachers at PMS |
| May/June 2019 |  | * Meet with administration and TLs regarding next steps at each school * Possible micro-credentialing | Administration, TLs, Dana, and Helen |

\* Touch base about the coaching in December.